PROJECT TIMELINE

DocExtract - Intelligent Document Processing

Document Control

| Field | Details |
| --- | --- |
| Project Name | DocExtract - Intelligent Document Processing |
| Document Title | Project Timeline (Gantt Chart) |
| Prepared By | DocExtract Project Team |
| Version | 1.0 |
| Date | 30 July 2026 |
| Project period | 24 June 2026 to 2 August 2026 (6 weeks) |
| Data source | Git repository history (first commit 24/06/2026, latest 27/07/2026) |

1. Summary

The project ran for six weeks, from 24 June to 2 August 2026. The chart below is reconstructed from the repository's commit history, so each bar shows when work actually landed rather than when it was scheduled. A solid bar marks the main work of that week; a light bar marks follow-up work or smaller fixes.

| Week | Dates | Main focus | Commits |
| --- | --- | --- | --- |
| W26 | 22-28 Jun | Project scaffolding, dataset, first extraction | 3 |
| W27 | 29 Jun-5 Jul | Interface, persistence, validation, export, evaluation, ROI | 24 |
| W28 | 6-12 Jul | Authentication, roles, audit, admin settings, RAG | 14 |
| W29 | 13-19 Jul | Model picker, persistent chat history | 4 |
| W30 | 20-26 Jul | Document refresh to v1.1, interface polish | 3 |
| W31 | 27 Jul-2 Aug | Archive and range export, testing, final documents, presentation | 1+ |

2. Gantt Chart

| Phase | Activity | Owner | W26 | W27 | W28 | W29 | W30 | W31 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 22-28 Jun | 29 Jun-5 Jul | 6-12 Jul | 13-19 Jul | 20-26 Jul | 27 Jul-2 Aug |
| Setup | Repository, backend and frontend scaffolding | Fadhil |  |  |  |  |  |  |
|  | Dummy dataset and ground-truth labels | Fazza |  |  |  |  |  |  |
|  | Model selection and LM Studio configuration | Gifari |  |  |  |  |  |  |
| Extraction | Extraction pipeline: pydantic schema and model call | Fadhil |  |  |  |  |  |  |
|  | Indonesian dot-thousands handling and date normalisation | Fadhil |  |  |  |  |  |  |
|  | Single-file and batch upload | Fadhil |  |  |  |  |  |  |
|  | Selectable extraction model (Qwen / MiniCPM / Gemini) | Gifari |  |  |  |  |  |  |
| Validation | Nine business rules with error and warning severities | Fadhil |  |  |  |  |  |  |
|  | Live validation panel on the review screen | Gifari |  |  |  |  |  |  |
|  | Admin-tunable validation thresholds | Fadhil |  |  |  |  |  |  |
| Interface | Frontend rebuilt on the design system | Gifari |  |  |  |  |  |  |
|  | Human-in-the-loop review screen | Gifari |  |  |  |  |  |  |
|  | Document list filters and pagination | Gifari |  |  |  |  |  |  |
|  | Layout and page padding polish | Gifari |  |  |  |  |  |  |
| Data | SQLite persistence and extraction caching | Fadhil |  |  |  |  |  |  |
|  | Authentication, roles and audit log | Fadhil |  |  |  |  |  |  |
|  | Admin user management | Fadhil |  |  |  |  |  |  |
| Export | CSV/JSON export and mock downstream API | Fadhil |  |  |  |  |  |  |
|  | Bulk export and selected-rows export | Fadhil |  |  |  |  |  |  |
|  | Archive: approved documents by approval date | Fadhil |  |  |  |  |  |  |
|  | Archive range export to PDF/Word/Excel/CSV/JSON | Fadhil |  |  |  |  |  |  |
| Evaluation | Field-level accuracy evaluation harness | Yazid |  |  |  |  |  |  |
|  | Admin-triggered evaluation and accuracy summary | Yazid |  |  |  |  |  |  |
|  | Model Speed page and processing-time measurement | Yazid |  |  |  |  |  |  |
| Business | ROI calculator and cost-benefit business case | Fazza |  |  |  |  |  |  |
| Bonus | RAG assistant and persistent chat history | Fadhil |  |  |  |  |  |  |
| Documents | Business Process Document and Database Design | Fazza |  |  |  |  |  |  |
|  | User Manual and Testing Scenario | Fazza |  |  |  |  |  |  |
|  | UI/UX Design and v1.2 document refresh | Fazza |  |  |  |  |  |  |
|  | End-to-end testing and evidence collection | Yazid |  |  |  |  |  |  |
|  | Final presentation deck | Fazza |  |  |  |  |  |  |

Legend:  solid blue = main work that week;  light blue = follow-up work or smaller fixes.

3. Milestones

| Date | Milestone | Evidence |
| --- | --- | --- |
| 24 Jun 2026 | First vertical slice working: upload, local extraction, results displayed | first commit in the repository |
| 30 Jun 2026 | Validation rules and their tests landed | validation + test commit |
| 1 Jul 2026 | CSV/JSON export, mock API, accuracy evaluation and ROI calculator complete, covering all six deliverables | 24 commits during W27 |
| 7 Jul 2026 | Real authentication, roles, RAG assistant and audit log | auth-roles-rag-audit commit |
| 8 Jul 2026 | Admin settings and user management | admin settings commit |
| 16 Jul 2026 | Persistent chat history | chat history commit |
| 26 Jul 2026 | Project documents refreshed to v1.1 | docs+ui commit |
| 27 Jul 2026 | Archive and range export to five formats | feat(archive) commit |
| 29-30 Jul 2026 | 150-scenario end-to-end testing, UI/UX design document, manual update | Works/3.Testing Scenario_v2.0.xlsx, Works/1.UI-UX Design.docx |

4. Notes

The Owner column reflects how the team divided the work by area. Note that most commits are recorded under a single account, so Git attribution does not always match the actual division of labour. Please confirm with each member before this document is finalised.

W29 and W30 look quieter because they coincided with document writing, which largely produces no code commits.

This chart records what happened, not what was originally planned. If a plan-versus-actual comparison is needed, the sprint plan on the Jira board can be added as a second set of rows.